## Sheet1
Tasks	Subtask	Description				Status/ / Github issue

1		Bring SAM4S definitions				1

2		Bring SAM4S-XPLD definitons				2

3		Bring tools support
	1	Bring ARM GCC support				3
	2	Bring em::blocks support				4
	3	Bring IAR EWARM support				5

4		Bring tools linker maps
	1	Bring ARM GCC linker map				3
	2	Bring em::blocks linker map (same as Task 4-1)				4
	3	Bring IAR EWARM linker map				5

5		Bring device/board inits at power up (clocks,etc...)				6

6		Bring some device peripheral drivers
	1	PMC
	2	EEFC
	3	PIO
	4	UART
	5	USART
	6	WDT
	7	PWM

7		Tests

8		Board documentation

9		Pull request

10		Bring more device peripheral drivers
	1	SPI
	2	TWI
	3	ADC
	4	TC
	5	UDP (USB device)
	6

11		Pull request 2

12		Let's play with LAB applications
	1	Wall harp
	2	Home automation
	3	Robotics
	4	3D printers
	5